IBPROM CORP Strategic Briefing Note Takeout and Delivery Revenue Optimization Boston Pizza — Gatineau, Quebec April 12, 2026 PREPARED FOR Dr. Diamandis PREPARED BY Joseph Soares, MBA, Adm.A., PMP Senior Advisor, IBPROM Corp PRIVILEGED AND CONFIDENTIAL

Executive Context

Dr. Diamandis, you asked me to examine how we could improve the performance of your takeout and delivery operations, given your strong results on Uber Eats, and whether that success could be reproduced on other platforms.

I have completed that analysis. What follows is not a narrow platform-by-platform comparison. As I reviewed the data, it became clear that the opportunity extends well beyond optimizing individual delivery apps. This briefing therefore takes a holistic, strategic view of the entire takeout and delivery revenue stream and presents a phased plan to maximize it.

This document is organized into three tiers of action:

- Immediate Actions — platform optimization steps that can be executed this week to recover revenue currently being lost on DoorDash and SkipTheDishes

- Near-Term Infrastructure — building the assets (website, social media, direct ordering) that will reduce platform dependency and improve margins within 60–90 days

- Strategic Positioning — a marketing and communications strategy that creates compounding, organic demand over time, making every paid dollar work harder

Current State of Delivery Operations

Your current daily delivery revenue across three platforms:

| Platform | Daily Revenue | Weekly Promo Spend | Performance |
| --- | --- | --- | --- |
| Uber Eats | $4,427 | $150/week | Strong |
| DoorDash | $210 | None | Critically Weak |
| SkipTheDishes | $109 | None | Very Weak |
| Total | $4,746/day | $150/week |  |

The core finding is this: your Uber Eats performance is excellent. Your DoorDash and SkipTheDishes performance is not merely weak — it is catastrophically below what these platforms should be producing for a restaurant with your Uber Eats volume. The gap represents the single largest revenue recovery opportunity in this analysis.

Part 1: Immediate Actions — Platform Recovery

These are steps that can be taken this week. They require no new technology, no capital investment, and no external vendors. They address revenue that is already flowing through these platforms to your competitors in Gatineau.

1.1 — DoorDash: The $90,000/Month Gap

Nationally, DoorDash holds approximately 30–35% of the Canadian food delivery market. Uber Eats holds 35–40%. For a restaurant generating $4,427 per day on Uber Eats, a properly performing DoorDash listing should produce between $2,800 and $3,800 per day. You are at $210. That is roughly 5–7% of your proportional potential.

At the midpoint, this represents approximately $3,000 per day in unrealized revenue — or $90,000 per month in top-line sales that is currently going to other restaurants in your delivery zone.

Probable causes of underperformance:

- Listing quality: incomplete menu, poor or missing photographs, weak descriptions

- Low review volume creating an algorithmic death spiral: low visibility produces fewer orders, which produces fewer reviews, which reduces visibility further

- Operational metrics: if prep times are long, cancellation rates are high, or order accuracy is low, DoorDash suppresses your ranking

- No promotional investment: unlike Uber Eats, no spend has been allocated to DoorDash to establish initial momentum

Immediate action items:

- Pull your DoorDash Merchant Portal analytics today. Identify your conversion rate, average rating, prep time, and cancellation rate. One or more of these metrics is killing your ranking.

- Compare your DoorDash listing side-by-side with your Uber Eats listing. The Uber listing almost certainly has better photos and a tighter, more curated menu. Replicate that standard on DoorDash.

- If you are on DoorDash’s Basic plan (15% commission), consider upgrading to Premier (30%) for 90 days. Premier includes automatic ads at no additional cost and a $200 professional photography credit. The higher commission reduces margin temporarily, but you need volume to escape the algorithm’s suppression cycle. Once you reach $1,500+ per day, reassess the plan.

- Ensure your hours of availability, delivery zone, and menu match or exceed what is listed on Uber Eats.

Target: $2,000–$3,500 per day within 60–90 days of sustained optimization. At a 30% commission and 30% food cost, this adds approximately $24,000–$42,000 per month in contribution margin.

1.2 — SkipTheDishes: The Secondary Recovery

SkipTheDishes holds approximately 15–20% of the Gatineau market. The francophone population may skew this slightly higher than the national average. Your proportional expectation is $1,500–$2,500 per day. At $109, you are in the same 5–7% capture range as DoorDash — which suggests a systemic issue, not a platform-specific one.

Immediate action items:

- Apply the same listing audit as DoorDash: photos, menu, descriptions, operational metrics

- Activate Skip’s “Free Delivery” promotion at $50–$75 per week for four weeks. Skip’s own data indicates up to 200% return on investment for this promotion type

- Consider “Top Placement” promotion, which Skip reports increases weekly views by 33.5% and can double order volume

Target: $800–$1,800 per day within 60–90 days. Combined with DoorDash recovery, this brings total daily delivery revenue from $4,746 to a potential range of $7,500–$9,700 per day.

1.3 — Uber Eats: Protect and Optimize

Your Uber Eats operation is performing well. Your $150 per week promotional spend is efficient — it is amplifying strong organic demand, not creating it. Do not increase this spend until DoorDash and SkipTheDishes are recovered. The return on fixing a broken channel far exceeds the return on optimizing a working one.

That said, there are incremental gains available:

- Refresh photographs. Uber’s own testing shows that relevant dish images in search results produce up to 32% more orders

- Review menu engineering: identify your highest-margin items and ensure they appear prominently

- Strategic promotional timing: concentrate spend on peak-demand periods (weekends, game nights, holidays) rather than spreading it evenly

Target: +$400–$650 per day through incremental optimization.

Part 2: Near-Term Infrastructure — Building Your Own Channel

The platforms are necessary, but they are expensive. At commission rates of 15–30%, every $100 in delivery revenue yields only $70–$85 after platform fees, before food cost. The strategic imperative is clear: build your own direct ordering channel where you retain 97% of revenue.

2.1 — A Dedicated Website for Boston Pizza Gatineau

Your location needs its own web presence — separate from the corporate Boston Pizza site. This is not about branding. It is about capturing the customers who already search for you by name and routing their orders through a channel you control.

When a customer in Gatineau types “Boston Pizza delivery” into Google, the result currently routes them to Uber Eats or DoorDash, where you pay 15–30% commission on the order. A dedicated website with integrated online ordering captures that same customer at a payment processing cost of approximately 2.9% + $0.30 per transaction. On a $35 average order, that is the difference between keeping $24.50 and keeping $33.50.

What the website needs:

- A clean, mobile-first design (over 70% of delivery orders originate on mobile devices)

- Integrated online ordering with payment processing

- Menu with photographs matching or exceeding your platform listings

- Your Google Business Profile linked directly to this ordering page

- French and English language capability for the Gatineau market

Cost: DoorDash offers a free Storefront product that provides a branded ordering page at 0% commission (payment processing fees only). This is the fastest, zero-cost path to a direct ordering channel. A custom website is a secondary consideration once volume justifies the investment.

2.2 — Google Business Profile and Google Food Ordering

This is the highest-impact, zero-cost action in this entire briefing after the DoorDash fix. Your Google Business Profile is the front door for every local search. When it includes an “Order Online” button that routes to your own ordering system rather than a third-party platform, every order that comes through it is at near-zero commission.

Google Food Ordering integrates directly into Google Maps and Google Search. The customer never leaves Google — they see your restaurant, click “Order,” and the transaction processes through your system. This captures demand that currently defaults to platform apps.

Target: $400–$900 per day in direct orders within 90–120 days. At 97% margin retention, the profit impact is equivalent to $1,500–$3,000 per day in platform revenue.

2.3 — Social Media Accounts

Your location should maintain its own social media presence — distinct from the corporate Boston Pizza accounts. The purpose is not vanity metrics. It is to create a local audience that you can reach directly, without paying platform fees or advertising costs, whenever you want to drive orders.

A Facebook page and Instagram account for Boston Pizza Gatineau, posting 3–5 times per week with food photography, local promotions, and community content, builds an organic audience that reduces your dependence on paid channels over time. This audience becomes the foundation for the strategy outlined in Part 3.

Part 3: Strategic Positioning — Organic First, Paid Second

This is the most important section of this briefing. The actions in Parts 1 and 2 will recover lost revenue and build new channels. But the long-term strategic advantage comes from the principle that governs how you invest in marketing going forward.

The principle is this: organic first, paid second.

Why Organic Must Come First

Organic content — social media posts, Google reviews, website content, local SEO — is created once and works indefinitely. A photograph of your best-selling pizza, posted to Instagram and optimized for Google, continues to attract customers for months or years after it is published. The marginal cost of each additional customer it attracts is zero.

Paid promotion — platform ads, sponsored listings, Google Ads — works only as long as you are paying for it. The moment the spend stops, the visibility disappears. It is punctual, not cumulative.

When you build a strong organic foundation first, your paid campaigns perform measurably better:

- Lower cost per click: Google’s Quality Score rewards advertisers whose landing pages and content are relevant and authoritative. A well-optimized website with genuine reviews and active social media presence reduces your ad costs

- Higher conversion rates: A customer who sees your ad, visits your website, and finds professional photos, genuine reviews, and an easy ordering experience converts at a higher rate than one who lands on a bare listing

- Compounding returns: Every piece of organic content strengthens your overall digital presence, which improves the performance of every paid dollar spent across every platform

The Marketing and Communications Strategy

What I am recommending is not a one-time campaign. It is a communications operating model for the location:

- Build the organic base (Weeks 1–12): Website live with ordering. Google Business Profile fully optimized. Social media accounts active with consistent posting. Review generation program in place (bag inserts, table cards, follow-up prompts).

- Layer paid promotion onto the organic base (Weeks 8–16): Platform promotions on DoorDash and Skip to accelerate recovery. Google Ads for “Boston Pizza delivery Gatineau” routing to your direct ordering page. Social media boosting of highest-performing organic posts.

- Optimize and scale (Ongoing): Measure cost per acquisition across every channel. Shift spend toward the highest-performing, lowest-cost channels. Continue building organic content that compounds over time.

By the time you activate paid campaigns, your organic foundation will be strong enough that every advertising dollar works harder than it would today. Your cost per click will be lower, your conversion rates will be higher, and your dependency on any single platform will be reduced.

Projected Revenue Impact

The following table summarizes the revenue opportunity across all three tiers of action:

| Action | Timeline | Daily Revenue Impact | Monthly Impact |
| --- | --- | --- | --- |
| Fix DoorDash | 60–90 days | +$2,000–$3,500/day | +$60K–$105K |
| Fix SkipTheDishes | 60–90 days | +$700–$1,500/day | +$21K–$45K |
| Optimize Uber Eats | Ongoing | +$400–$650/day | +$12K–$20K |
| Direct ordering channel | 90–120 days | +$400–$900/day | +$12K–$27K |
| Total Potential Uplift |  | +$3,500–$6,550/day | +$105K–$197K |

If these projections are realized at even 60% of the midpoint, your total daily delivery revenue moves from approximately $4,746 to over $9,500 per day — a near-doubling of the delivery revenue stream. The direct ordering channel, though smaller in absolute terms, contributes disproportionately to the bottom line because of its dramatically higher margin retention.

A Note on Additional Platforms

I examined every delivery platform operating in the Gatineau-Ottawa region, including Fantuan (Asian-community focused), Quickmarket (local Ottawa-Gatineau platform), Ritual (order-ahead, primarily Toronto), and several Quebec-specific options. None of them warrant activation at this time. Their combined user base in Gatineau is too small to justify the operational overhead of an additional tablet, menu, and order management stream. The delivery market in this region is a three-platform market — Uber Eats, DoorDash, and SkipTheDishes — plus your own direct channel. That is where the revenue is.

Closing Observation

The mandate you gave me was to examine how your Uber Eats success could be replicated on other platforms. The answer is straightforward: apply the same operational discipline and listing quality to DoorDash and SkipTheDishes that you have applied to Uber Eats. The revenue will follow.

But the larger opportunity — the one I would be failing my duty not to raise — is that you are building on rented land. Every dollar earned through a third-party platform is subject to their commission structure, their algorithm, and their terms. Building your own digital infrastructure — website, direct ordering, social media, organic search presence — is how you take control of that revenue stream permanently.

I am available to discuss this briefing at your convenience and to support implementation of any or all of the actions outlined above.

Respectfully,

Joseph Soares, MBA, Adm.A., PMP

Senior Advisor, IBPROM Corp

j@josephsoares.com